## Status
Session | Status | When | Duration | Commits | Headline
S0 (sprint-0) | Done | 14 May 19:30 → 23:24 EAT | ~4 hours | 12 | Sprint 0 deliverables per SAD §11.4: scaffold, schema, UBOS loader, DAT-DQA, DAT-DDUP tier 1, DIH framework, OpenAPI skeletons, CI, NIRA mock, threat model + DPIA draft.
S1 | Done | 15 May 00:20 → 05:10 EAT | ~5 hours | 10 | Hardening: DRF auth, real NIN encryption, safe boot, fast-track sampling, audit emitter unification + Postgres audit tests, sub-region partitioning (ADR-0005), design chips, ChangeRequest + UPD scaffold, PMT v1 scaffold.
S2 | Done | 15 May 05:21 → 05:47 EAT | ~26 minutes | 6 | ABAC + audit middleware + DDUP tier 2 phone matcher + INT Submission scaffold + GRM L1/L2 + programme referral.
S3 | Done | 15 May 07:09 → 09:43 EAT | ~2.5 hours | 6 | RPT scaffold, API-DRS scaffold, vital-event auto-commit + 1% sampling, SLA-breach surfacing, PDM connector, NIRA client seam.
S4 | Done | 15 May 2026 | open | 3 | Partner-side ABAC on API-DRS, NUSAF connector, routing matrix → REF-DATA (UPD-O-01 resolved). Subsumed into S5+ sprint sequence.
S5 | Planned | next session | TBD | 0 | Likely scope: tier-3 DDUP (probabilistic) scaffold (post-calibration), full UPD review screen wiring (US-090, AC-UPD-PMT-PREVIEW), citizen receipt SMS, PMT v0 model definition file, OpenAPI populate per module.
S6 | Planned | next + 1 | TBD | 0 | DSA enforcement on DRS extract delivery (Excel/CSV/API channels), DPO console (US-103), partner password-email channel.
S7 | Planned | next + 2 | TBD | 0 | Pilot prep: ops runbooks, observability dashboards, DR drill, training material, MVP cut tag.
S27 | Done | 26 May EAT | ~1 hour | 2 | UPD workbench history view: Decided + On-hold tabs on the change-request screen, manual ?status= filter on /api/v1/upd/change-requests/ (django-filter no-op workaround), Social Registry Manager role added to Tweaks role switcher for approver-persona demos. 5 new pytest filter tests; full UPD suite + 204 JS tests green.
S5+S6 | Done | 2026-05-15 | ~1 day | ~30 | UPD ChangeRequest admin workbench (US-S5-001), API-DRS export-bundle render (US-S5-002), DDUP merge REVERSED state (US-S5-003), DIH WFP SCOPE connector (US-S5-004), IDV NIRA queue+retry (US-S5-005), API-DRS expiry sweep (US-S5-006). See dpia/sprint_5_6_impacts.md
S7 | Done | 2026-05-15 | ~half day | ~15 | UPD auto-escalation on SLA breach, DIH NIRA reverse-feed (vital events), DDUP tier 3 probabilistic discovery, DRS partner /requests/mine/, RPT CSV exports, ADR-0006 Keycloak realm. See dpia/sprint_7_impacts.md
S8 | Done | 2026-05-15 | ~half day | ~12 | DDUP tier-3 auto-merge confidence rule, DRS partner download endpoint, RPT weekly registrations dashboard, DIH connector framework, GRM workbench (first React screen). See dpia/sprint_8_impacts.md
S9 | Done | 2026-05-15 | ~half day | ~12 | DDUP MatchPair admin per_field_scores, RPT grievances-by-category dashboard, DRS throttling, GRM → UPD cross-screen handoff, DRS partner portal screen. See dpia/sprint_9_impacts.md
S10+S11 | Done | 2026-05-15 | ~1 day | ~20 | Tweaks panel reopen pill, DDUP reverse-merge counters, Partner DRS request-builder (third React screen), UPD bulk-action endpoints, DIH ConnectorRun admin. See dpia/sprint_10_11_impacts.md
S12 | Done | 2026-05-16 | ~half day | ~10 | Home-screen KPIs from live counts, live Audit chain + Updates history tabs on household detail, Celery beat for pending Kobo landings. See dpia/sprint_12_impacts.md
S13 | Done | 2026-05-16 | ~half day | ~10 | Adopt claude.ai Registry + Household redesign, wire home queue panels live, DDUP screen live, DRS partner list live. See dpia/sprint_13_impacts.md
S14 | Done | 2026-05-15 | ~half day | ~10 | Merge-via-REST + DDUP React Merge loop, DRS operator list live, Programmes + Grievances tabs on household detail, per-region home drill-down. See dpia/sprint_14_impacts.md
S15 | Done | 2026-05-15 | ~half day | ~8 | DDUP merge modal "Reversible until <date>", DRS operator avg decision turnaround, region drill-down extended to queue panels, ADR-0008 pagination+throttling sweep. See dpia/sprint_15_impacts.md
S16 | Done | 2026-05-15 | ~half day | ~8 | Audit-reason enrichment, partner DRS typical wait time, Member endpoint max_page_size cap, audit-chain integrity scheduled job. See dpia/sprint_16_impacts.md
S17+S18 | Done | 2026-05-15 | ~1 day | ~15 | DDUP merge modal per-field similarity, home dashboard drill-down breadcrumb, DRS partner builder DSA-driven field disabling, US-082b RPT violations dashboard, US-082c failures_7d on DqaRule. See dpia/sprint_17_18_impacts.md
S19 | Done | 2026-05-15 | ~1 day | ~15 | ChoiceList + ChoiceOption catalogue (US-116), FormSection/Question/SkipLogic/Constraint models (US-117a), questionnaire builder admin UI (US-117b), XLSForm export (US-118), rule-pack sync (US-119), legacy questionnaire import (US-120). See dpia/sprint_19_impacts.md
S20 | Done | 2026-05-17 | ~half day | ~6 | PII-shape lint for constraint messages (US-S20-001), gate SQLite-only audit-chain tests on Postgres CI (US-S20-003), push FormVersion xlsx to Kobo (US-S20-004), lock active forms + clone-to-new-draft (US-S20-005), wire XLSForm geo selects to GeographicUnit (US-S20-006). (No dpia file — minimal personal-data surface.)
S21 | Done | 2026-05-18 | ~half day | ~6 | GRM workbench live API wiring (US-S21-002), GrievanceTask + resolve gate (US-S21-003), task visibility scoping (US-S21-004), persist + display resolve/close narrative (US-S21-005), Kobo missing-calculation fix (US-S21-006). (No dpia file — minimal personal-data surface.)
S22 | Done | 2026-05-19 | ~1 day | ~25 | UPD workbench live + Open-CR modal (US-S22-001..004), drop TextChoices on coded fields + resolver/serializer label fields + bundle endpoint + JSX wiring (US-S22-005a..g), connectors + registry JSX + UPD field-catalog corrections (US-S22-005h..j). See dpia/sprint_22_impacts.md
S22-DE | Done | 2026-05-19 | ~1 day | ~15 | Detail entities — 14 new tables capturing per-section questionnaire repeats (health, education, employment, dwelling, utilities, food, shock, coping). Special-category data review per DPPA 2019 §§9–10. See dpia/sprint_22_detail_entities_impacts.md
S23 | Done | 2026-05-19 | ~1 day | ~15 | Partners module — Partner + PartnerContact models (US-S23-004..005), DataSharingAgreement + DsaSignature (US-S23-006), signature workflow (US-S23-010), PartnerUsageDaily + activity projection (US-S23-007), API surface (US-S23-008..009), lint gate + e2e tests (US-S23-014..015). See dpia/sprint_23_impacts.md
S24 | Done | 2026-05-19 | ~half day | ~6 | Canonical Partner + DSA consolidation — lift DRS-local rows to apps.partners (US-S24-002), schema swap + canonical enforcement (US-S24-003..004). See dpia/sprint_24_impacts.md
S25 | Done | 2026-05-19 | ~half day | ~5 | Programme registration wizard — ChoiceLists seeded (US-S25-001), Programme model extension (US-S25-002), CRUD endpoint (US-S25-003), wizard JSX wired to live API (US-S25-004), lint gate + integration tests (US-S25-005). See dpia/sprint_25_impacts.md
S26 | Done | 2026-05-20 | ~half day | ~8 | apps.referral.Programme consolidation — ADR-0015 (US-S26-001), referral_status ChoiceList seeded (US-S26-002), strip TextChoices + align enrolment codes (US-S26-003), lift Programme rows to canonical (US-S26-004), schema swap + drop legacy (US-S26-005), /api/v1/beneficiaries/ listing (US-S26-006). See dpia/sprint_26_impacts.md
S26b | Done | 2026-05-21 → 2026-05-26 | ~5 days | ~80 | Post-S26 iterations consolidated in this backfill: chatbot module (US-CHB-001..006), Open-CR modal slices (member picker, supporting docs, step wizard, before/after diff), DIH walk-in path + Quality-Failed archive + inline correction + reprocess workflow, source-of-truth audit, user manual mkdocs scaffold, refdata duplicate cleanup, home dashboard wiring fixes, chatbot Assistant in admin console, PMT signoff rejection terminal + PMT Configuration live wiring + unified Approvals queue. (Several commits not US-tagged — see git log.)
S27→S28 | Done | 2026-05-30 → 2026-05-31 | ~1 day | 23 | Consent Management module (Epic 19, US-CONSENT-01..18) — apps/consent behind CONSENT_MODULE_ENABLED. Catalogue + dual-approval, statement versioning, capture (walk-in/CAPI/Kobo + citizen portal), withdrawal flow + DPO queue + SLA sweep, gates into PMT/REF/DRS/DDUP/UPD/DIH/INT, audit chain, DQA rule pack, ADR-0024 + DPIA §14 + OpenAPI. Live-wired citizen screen (capture/withdraw/history) + per-purpose capture form + household Consent tab card. Also fixed pre-existing CI (bandit, JS, E004 check, dob matview migration, replica routing). 1820 py tests / 228 JS / 6-of-7 CI green; remaining pytest reds are pre-existing data_explorer/dqa debt (zero consent).

## Story Map
Session Story | Commit | Status | Backlog ID(s) | Module | Notes
sprint-0/scaffold | db47b76 | Done | US-069 | All | Django 5 + DRF + 15 module apps.
sprint-0/schema | 76e950c | Done | US-011, US-012 | DAT | Household + Member + paired version tables.
sprint-0/docker | 243f89b | Done | (infra) | All | Dockerfile, docker-compose, .dockerignore.
sprint-0/admin | fefb7d5 | Done | (infra) | DAT, SEC, REF-DATA | Django admin registrations for Household, Member, GeographicUnit, AuditEvent.
sprint-0/ubos-loader | 21f4584 | Done | (REF-DATA) | REF-DATA | UBOS geographic hierarchy loader (SAD §11.4 item 3).
sprint-0/dqa-engine | 8d9167c | Done | US-076, US-077, US-078, US-079 | DAT-DQA | Rules engine + dual approval + AC-MANDATORY/AC-NIN-FORMAT/AC-GPS-ACCURACY wired.
sprint-0/ddup-tier1 | 39cda81 | Done | US-082, US-083, US-084, US-087 | DAT-DDUP | NIN matcher + merge transaction + dual-approved match-model versioning.
sprint-0/dih-framework | 630f225 | Done | US-105, US-106, US-107, US-108 | DIH | SourceSystem + pipeline + atomic promotion API.
sprint-0/openapi-skeletons | 265134a | Done | US-041 | API | OpenAPI 3.1 skeletons per module + v2 UBOS loader.
sprint-0/ci-pipeline | 5085cd8 | Done | US-072 | DevOps | GitHub Actions + ruff/pytest/spectacular hygiene.
sprint-0/nira-mock | 3f80e71 | Done | (IDV) | IDV | /api/v1/idv/nira-mock/verify sandbox; gates DEP-02 mitigation.
sprint-0/threat-dpia | 6ce1d52 | Done | (DEP-09, DEP-17) | Cross-cutting | Threat model + DPIA initial draft. Critical pre-pilot deliverable.
US-S1-001 | 20c2e90 | Done | US-042 | SEC | DRF authentication + IsAuthenticated default.
US-S1-002 | b72745e | Done | US-071 | SEC | Real NIN encryption + canonical hash on promote (per ADR-0002).
US-S1-003 | fbd6f41 | Done | (NFR) | SEC | Safe boot (Postgres required, NIRA mock fenced, .env example).
US-S1-004 | f14177c | Done | US-111 (AC-DIH-FT-AUTO) | DIH | 1% audit sampling on fast-tracked walk-ins.
US-S1-005 | c6a0a2b | Done | US-066 | SEC | Single audit emitter, drop dead branches + shims.
US-S1-006 | d51fe91 | Done | US-066 | SEC | Postgres-only audit-chain integration tests.
US-S1-007 | 2f821b8 | Done | SAD §5.5 | DAT | sub_region_code partition key + ADR-0005 (new).
US-S1-008 | 46bece8 | Done | US-083, US-098 | Design | Chip vocabulary, dedup a11y radio group, screens 8 + 9.
US-S1-009 | 1820bf6 | Done | US-027, US-088, US-089, US-090, US-091, US-092 | UPD | ChangeRequest + UPD workflow scaffold (foundational).
US-S1-010 | 41da090 | Done | US-022, US-023 | PMT | PMT v1 scaffold with dual-approved model + recompute event.
US-S2-001 | ae5fbdf | Done | US-066, US-072 | SEC | Read-side audit middleware on every personal-data viewset.
US-S2-003 | fbd04a6 | Done | US-063, US-064 | SEC | ABAC geographic scope on Household + Member reads.
US-S2-006 | 53c425d | Done | US-001, US-005, US-008 | INT | Submission entity + intake form scaffold.
US-S2-007 | e769303 | Done | (DDUP tier 2) | DAT-DDUP | Tier 2 deterministic phone matcher (E.164).
US-S2-008 | 16d5e70 | Done | US-032, US-033, US-034 | GRM | GRM intake at L1 and L2 with manual escalation.
US-S2-009 | b3214d1 | Done | US-037, US-038, US-039 | REF | Programme referral (Sprint 2 MVP).
US-S3-001 | cdb5842 | Done | US-047 | RPT | RPT scaffold + first three dashboards.
US-S3-002 | e5d2381 | Done | US-052, US-053, US-097 | API-DRS | API-DRS scaffold (Partner / DSA / DataRequest).
US-S3-003 | 8eb9daf | Done | US-020, US-021, US-096 | UPD | Vital-event auto-commit + 1% sample policy.
US-S3-004 | d0d4756 | Done | US-095 | GRM, RPT | SLA-breach surfacing for supervisors.
US-S3-005 | 76e6607 | Done | US-039, DEP-05 mitigation | DIH | PDM (Parish Development Model) connector.
US-S3-006 | a3ed464 | Done | US-017 | IDV | NIRA client seam (mock/live provider switch).
US-S4-001 | 1920eb3 | Done | US-054 | API-DRS, SEC | Partner-side ABAC on API-DRS.
US-S4-002 | 90147d7 | Done | US-039 (NUSAF) | DIH | NUSAF connector (mirrors PDM).
US-S4-003 | fdbd1fe | Done | US-089, UPD-O-01 | UPD, REF-DATA | Routing matrix moves to REF-DATA. Open item UPD-O-01 closed.
(tween) DIH orchestrator | 29799ba | Done | US-108 | DIH | Pipeline orchestrator — DQA -> IDV -> DDUP -> route / fast-track.
(tween) Landing page | 4d3287f | Done | (devx) | All | Landing page at / listing admin + API entry points.
(tween) ABAC generalisation | 7d35e00 | Done | US-063 | SEC | Generalise ABAC scope to FK-related models (Referral, Enrolment).
(tween) ABAC extra | cd1f1f2, 7ded5e6, 90bc44c | Done | US-063 | SEC | ABAC scope on Submission, Grievance, StageRecord, PMTResult, ChangeRequest, MatchPair.
(tween) GRM ↔ UPD link | 572531b | Done | US-094 (AC-UPD-GRM-LINK) | GRM, UPD | GRM and UPD bidirectional linkage per SAD §4.4.
(tween) Test fixes | 06f7cc1, 23e352d, 1d91965 | Done | (stability) | All | Postgres trigger handling, DQA numeric coercion.
(tween) CI hygiene | 9c1883a, dc50cce, a9b0ea6, 5c447d0, 1a77211, a4b1702 | Done | US-072 | DevOps | pip-audit + bandit configuration + ruff cleanup.
S27/srm-role | (pending) | Done | (design persona) | SEC, UPD | Social Registry Manager added to Tweaks role switcher — approver persona for demoing AC-UPD-NO-SELF-APPROVE flows without swapping accounts.
S27/upd-history-tabs | (pending) | Done | US-S22-001 | UPD | Decided + On-hold tabs on the change-request workbench. Manual ?status= filter in ChangeRequestViewSet.get_queryset() — filterset_fields was silently a no-op (django-filter not installed). +5 pytest filter tests.
S5+S6/all | (dpia) | Done | US-S5-001..006 | UPD, API-DRS, DDUP, DIH, IDV | See dpia/sprint_5_6_impacts.md
S7/all | (dpia) | Done | US-S7-001..006 | UPD, DIH, DDUP, DRS, RPT, SEC | See dpia/sprint_7_impacts.md
S8/all | (dpia) | Done | US-S8-001..006 | DDUP, DRS, RPT, DIH, GRM | See dpia/sprint_8_impacts.md
S9/all | (dpia) | Done | US-S9-001..006 | DDUP, RPT, DRS, GRM, UPD | See dpia/sprint_9_impacts.md
S10+S11/all | (dpia) | Done | US-S10-001..006 | design, DDUP, DRS, UPD, DIH | See dpia/sprint_10_11_impacts.md
S12/all | (dpia) | Done | US-S12-001..005 | design, household, DIH | See dpia/sprint_12_impacts.md
S13/all | (dpia) | Done | US-S13-001..005 | design, home, DDUP, DRS | See dpia/sprint_13_impacts.md
S14/all | (dpia) | Done | US-S14-001..005 | DDUP, DRS, household, home | See dpia/sprint_14_impacts.md
S15/all | (dpia) | Done | US-S15-001..005 | DDUP, DRS, home, API | See dpia/sprint_15_impacts.md
S16/all | (dpia) | Done | US-S16-001..005 | SEC, DRS, DAT, audit | See dpia/sprint_16_impacts.md
S17+S18/all | (dpia) | Done | US-082b/c, US-S18-001..003 | DAT-DQA, design, DDUP, DRS | See dpia/sprint_17_18_impacts.md
S19/all | (dpia) | Done | US-116..120 | REF-DATA, INT, DAT-DQA | See dpia/sprint_19_impacts.md
S20/all | (git) | Done | US-S20-001/003..006 | INT, SEC, REF-DATA | XLSForm + Kobo push + audit-test CI gate.
S21/all | (git) | Done | US-S21-002..006 | GRM, INT | GRM workbench live + GrievanceTask + resolve gate.
S22/all | (dpia) | Done | US-S22-001..005 | UPD, REF-DATA, design | See dpia/sprint_22_impacts.md
S22-DE/all | (dpia) | Done | US-S22-DE | DAT (detail entities) | See dpia/sprint_22_detail_entities_impacts.md
S23/all | (dpia) | Done | US-S23-004..015 | partners, SEC | See dpia/sprint_23_impacts.md
S24/all | (dpia) | Done | US-S24-002..004 | partners | See dpia/sprint_24_impacts.md
S25/all | (dpia) | Done | US-S25-001..005 | referral, design | See dpia/sprint_25_impacts.md
S26/all | (dpia) | Done | US-S26-001..006 | referral, REF-DATA, beneficiaries | See dpia/sprint_26_impacts.md
S26b/chatbot | (this backfill) | Done | US-CHB-001..006 | chatbot | RAG over user manuals; Anthropic + sentence-transformers; ADR-0021.
S26b/open-cr-modal | (this backfill) | Done | (UPD UI slices) | UPD, design | Member picker, supporting docs, step wizard, before/after diff.
S26b/dih-walkin | (this backfill) | Done | (DIH UX iterations) | DIH | Walk-in submit + Quality-Failed archive + inline correction + reprocess workflow.
S26b/user-manual | (this backfill) | Done | (docs) | docs | mkdocs-material scaffold under /docs/user-manual served via Django /manual/.
S26b/source-of-truth | (this backfill) | Done | (docs) | docs | Four-pillar audit (truth, cascade, hardcoded, duplicates) — all PASS.
S26b/pmt-reject-terminal | (this backfill) | Done | (PMT lifecycle) | PMT, admin_console | Rejection now terminal; signoffs + audit row preserved.
S26b/pmt-config-live | (this backfill) | Done | (PMT UI) | PMT, design | Configuration screen wired to /api/v1/admin/pmt/versions/.
S26b/approvals-queue | (this backfill) | Done | (cross-module queue) | admin_console | Unified /api/v1/admin/approvals/ across CL, DQA, PMT.
S26b/admin-polish | (this backfill) | Done | (admin UI) | admin_console, design | Null-safe DDUP, live CL detail, DQA descriptions, refdata-geography search reset.
S27/consent-foundation | 28b7167 | Done | US-CONSENT-01/02/10/18 | Consent (SEC) | App scaffold, 8-table model, dual-approval catalogue, audit wiring, ADR-0024 + DPIA §14.
S27/consent-rules-sla | b646e5b | Done | US-CONSENT-07/09 | Consent (SEC), DAT-DQA | AC-CONSENT-* rule pack (DRAFT), SLA beat sweep, CONSENT-O-01 vocab reconcile (ELIGIBILITY).
S28/consent-propagation | c862b33 | Done | US-CONSENT-12/13/15/16 | PMT, REF, DDUP, UPD | Consent gates wired into PMT/REF/DDUP/UPD.
S28/consent-dih-dash | 81b7da4 | Done | US-CONSENT-11/17 | DIH, Consent (SEC) | DIH fast-track synthetic consent + DPO coverage stub.
S28/consent-drs | 99c1541 | Done | US-CONSENT-14 | API-DRS | DRS extract row-level consent gate (SQL).
S28/consent-frontend | 4d4e13d..eef6e6b | Done | US-CONSENT-03/05/08 | Consent (SEC), design | Admin console screens + citizen portal + badge cluster + live-wired citizen screen + per-purpose capture form.
S28/consent-intake | 278c54c, 581833f | Done | US-CONSENT-03 | INT, DIH | Intake gate + capture (walk-in/CAPI/Kobo); capture form replaces legacy toggle.

## Backlog Status
Backlog ID | Status | Delivered by | Priority | Epic | Module | Notes
US-001 | Done | US-S2-006 | Must | 1. Intake & Registration | Intake & Registration | Submission entity scaffolded; CAPI offline path deferred to S5+.
US-002 | Not started |  | Must | 1. Intake & Registration | Intake & Registration
US-003 | Not started |  | Should | 1. Intake & Registration | Intake & Registration
US-004 | Not started |  | Must | 1. Intake & Registration | Intake & Registration
US-005 | Done | US-S2-006 | Must | 1. Intake & Registration | Intake & Registration | Submission + intake form scaffold.
US-006 | Not started |  | Must | 1. Intake & Registration | Intake & Registration
US-007 | Not started |  | Could | 1. Intake & Registration | Intake & Registration
US-008 | Done | US-S2-006 | Must | 1. Intake & Registration | Intake & Registration | Bulk import path via DIH connector framework.
US-009 | Not started |  | Should | 1. Intake & Registration | Intake & Registration
US-010 | Not started |  | Must | 1. Intake & Registration | Intake & Registration
US-011 | Done | sprint-0/schema | Must | 2. Household & Individual Data Management | Data Management | Versioned tables in place.
US-012 | Done | sprint-0/schema | Must | 2. Household & Individual Data Management | Data Management | Single golden record pattern.
US-013 | Not started |  | Must | 2. Household & Individual Data Management | Data Management
US-014 | Not started |  | Should | 2. Household & Individual Data Management | Data Management
US-015 | Not started |  | Must | 2. Household & Individual Data Management | Data Management
US-016 | Not started |  | Must | 2. Household & Individual Data Management | Data Management
US-017 | Done | US-S3-006 | Must | 3. Identity Verification (NIRA) | Identity Verification | NIRA client seam in place; live MoU pending DEP-02.
US-018 | Not started |  | Must | 3. Identity Verification (NIRA) | Identity Verification
US-019 | Not started |  | Must | 3. Identity Verification (NIRA) | Identity Verification
US-020 | Done | US-S3-003 | Should | 3. Identity Verification (NIRA) | Identity Verification | Vital-event auto-commit policy live.
US-021 | Done | US-S3-003 | Must | 3. Identity Verification (NIRA) | Identity Verification | Same policy covers reassessment trigger.
US-022 | Partial | US-S1-010 | Must | 4. PMT & Eligibility Assessment | Eligibility & Targeting | PMT model scaffold; calibrated weights pending DEP-03/DEP-04.
US-023 | Done | US-S1-010 | Must | 4. PMT & Eligibility Assessment | Eligibility & Targeting | PMT recompute event wired.
US-024 | Not started |  | Must | 4. PMT & Eligibility Assessment | Eligibility & Targeting
US-025 | Not started |  | Should | 4. PMT & Eligibility Assessment | Eligibility & Targeting
US-026 | Not started |  | Should | 4. PMT & Eligibility Assessment | Eligibility & Targeting
US-027 | Partial | US-S1-009 | Must | 5. Dynamic Updates & Recertification | Update Management | ChangeRequest scaffold; citizen-side reporting deferred.
US-028 | Not started |  | Must | 5. Dynamic Updates & Recertification | Update Management
US-029 | Not started |  | Must | 5. Dynamic Updates & Recertification | Update Management
US-030 | Not started |  | Must | 5. Dynamic Updates & Recertification | Update Management
US-031 | Not started |  | Should | 5. Dynamic Updates & Recertification | Update Management
US-032 | Done | US-S2-008 | Must | 6. Grievances & Correction Requests | Grievance Redress (GRM) | GRM L1 intake live.
US-033 | Done | US-S2-008 | Must | 6. Grievances & Correction Requests | Grievance Redress (GRM) | Triage + route via L1/L2.
US-034 | Done | US-S2-008 | Must | 6. Grievances & Correction Requests | Grievance Redress (GRM) | Link to ChangeRequest via tween (572531b).
US-035 | Not started |  | Should | 6. Grievances & Correction Requests | Grievance Redress (GRM)
US-036 | Not started |  | Must | 6. Grievances & Correction Requests | Grievance Redress (GRM)
US-037 | Done | US-S2-009 | Must | 7. Programme Referral & Enrolment | Programme Referral & Enrolment | Programme referral pull.
US-038 | Done | US-S2-009 | Should | 7. Programme Referral & Enrolment | Programme Referral & Enrolment | Referral creation.
US-039 | Done | US-S2-009, US-S3-005, US-S4-002 | Must | 7. Programme Referral & Enrolment | Programme Referral & Enrolment | Programme MIS notify path; PDM + NUSAF connectors.
US-040 | Not started |  | Should | 7. Programme Referral & Enrolment | Programme Referral & Enrolment
US-041 | Done | sprint-0/openapi-skeletons | Must | 8. Interoperability & API Gateway | API Gateway & Integrations | Versioned API surface + spectacular.
US-042 | Done | US-S1-001 | Must | 8. Interoperability & API Gateway | API Gateway & Integrations | OAuth client credentials path (DRF auth).
US-043 | Not started |  | Must | 8. Interoperability & API Gateway | API Gateway & Integrations
US-044 | Not started |  | Should | 8. Interoperability & API Gateway | API Gateway & Integrations
US-045 | Not started |  | Should | 8. Interoperability & API Gateway | API Gateway & Integrations
US-046 | Not started |  | Must | 8. Interoperability & API Gateway | API Gateway & Integrations
US-047 | Done | US-S3-001 | Must | 9. Reporting & Analytics | Reporting & Analytics | Coverage dashboard scaffolded.
US-048 | Done | reporting-refresh | Should | 9. Reporting & Analytics | Reporting & Analytics | PMT bands chart and horizontal household distribution now live.
US-049 | Done | reporting-refresh | Should | 9. Reporting & Analytics | Reporting & Analytics | Pipeline funnel and DRS status views now live.
US-050 | Done | reporting-refresh | Must | 9. Reporting & Analytics | Reporting & Analytics | Dedup status views and DQA violation record downloads now live.
US-051 | Done | reporting-refresh | Should | 9. Reporting & Analytics | Reporting & Analytics | Weekly registrations/submissions trends, export controls, and role-aware error states now live.
US-052 | Done | US-S3-002 | Must | 10. Data Requests & Sharing Management | Data Requests & Sharing | External requester baseline (Partner/DSA/DataRequest).
US-053 | Done | US-S3-002 | Must | 10. Data Requests & Sharing Management | Data Requests & Sharing | Steward review path scaffolded.
US-054 | Done | US-S4-001 | Must | 10. Data Requests & Sharing Management | Data Requests & Sharing | DSA enforcement via partner-side ABAC.
US-055 | Not started |  | Must | 10. Data Requests & Sharing Management | Data Requests & Sharing
US-056 | Not started |  | Must | 10. Data Requests & Sharing Management | Data Requests & Sharing
US-057 | Not started |  | Should | 10. Data Requests & Sharing Management | Data Requests & Sharing
US-058 | Not started |  | Must | 11. Single Registry / Beneficiary Data Exchange | Single Registry Linkage
US-059 | Not started |  | Must | 11. Single Registry / Beneficiary Data Exchange | Single Registry Linkage
US-060 | Not started |  | Must | 11. Single Registry / Beneficiary Data Exchange | Single Registry Linkage
US-061 | Not started |  | Should | 11. Single Registry / Beneficiary Data Exchange | Single Registry Linkage
US-062 | Not started |  | Must | 11. Single Registry / Beneficiary Data Exchange | Single Registry Linkage
US-063 | Done | US-S2-003 + tween | Must | 12. User, Role, Consent & Audit | Identity, Access, Consent, Audit | ABAC across personal-data entities.
US-064 | Done | US-S2-003 | Must | 12. User, Role, Consent & Audit | Identity, Access, Consent, Audit | Account-level enforcement via ABAC.
US-065 | Not started |  | Must | 12. User, Role, Consent & Audit | Identity, Access, Consent, Audit
US-066 | Done | US-S1-005, US-S1-006, US-S2-001 | Must | 12. User, Role, Consent & Audit | Identity, Access, Consent, Audit | Audit emitter + chain tests + read-side middleware.
US-067 | Not started |  | Must | 12. User, Role, Consent & Audit | Identity, Access, Consent, Audit
US-068 | Not started |  | Must | 12. User, Role, Consent & Audit | Identity, Access, Consent, Audit
US-069 | Done | sprint-0/scaffold | Must | 13. System & Non-Functional | Platform, Performance, Operations | Django/K8s-ready scaffold.
US-070 | Not started |  | Must | 13. System & Non-Functional | Platform, Performance, Operations
US-071 | Done | US-S1-002 | Must | 13. System & Non-Functional | Platform, Performance, Operations | NIN encryption + hash per ADR-0002.
US-072 | Done | sprint-0/ci-pipeline, US-S2-001 + tween | Must | 13. System & Non-Functional | Platform, Performance, Operations | Observability (audit + CI).
US-073 | Not started |  | Should | 13. System & Non-Functional | Platform, Performance, Operations
US-074 | Not started |  | Should | 13. System & Non-Functional | Platform, Performance, Operations
US-088 | Partial | US-S1-009 | Must | 5. Dynamic Updates & Recertification | Update Management | ChangeRequest scaffold; walk-in UI deferred.
US-089 | Done | US-S1-009, US-S4-003 | Must | 5. Dynamic Updates & Recertification | Update Management | Routing matrix in REF-DATA. UPD-O-01 closed.
US-090 | Partial | US-S1-009 | Must | 5. Dynamic Updates & Recertification | Update Management | Review screen wiring deferred to S5.
US-091 | Partial | US-S1-009 | Must | 5. Dynamic Updates & Recertification | Update Management | No-self-approve enforcement pending.
US-092 | Done | US-S1-009 | Must | 5. Dynamic Updates & Recertification | Update Management | Commit transaction in scaffold.
US-093 | Not started |  | Must | 5. Dynamic Updates & Recertification | Update Management
US-094 | Done | tween 572531b | Should | 5. Dynamic Updates & Recertification | Update Management | GRM ↔ UPD auto-close.
US-095 | Done | US-S3-004 | Should | 5. Dynamic Updates & Recertification | Update Management | SLA Breach dashboard.
US-096 | Done | US-S3-003 | Should | 5. Dynamic Updates & Recertification | Update Management | NIRA vital-event auto-commit.
US-076 | Done | sprint-0/dqa-engine | Must | 14. Data Quality Assessment | DAT-DQA | Rule CRUD.
US-077 | Done | sprint-0/dqa-engine | Must | 14. Data Quality Assessment | DAT-DQA | Rule preview scaffolded.
US-078 | Done | sprint-0/dqa-engine | Must | 14. Data Quality Assessment | DAT-DQA | Dual approval.
US-079 | Done | sprint-0/dqa-engine | Must | 14. Data Quality Assessment | DAT-DQA | Rule evaluation on ingest.
US-080 | Not started |  | Must | 14. Data Quality Assessment | DAT-DQA
US-081 | Not started |  | Should | 14. Data Quality Assessment | DAT-DQA
US-082 | Done | sprint-0/ddup-tier1 | Must | 15. Deduplication & Record Matching | DAT-DDUP | Dedup dashboard scaffolded.
US-083 | Done | sprint-0/ddup-tier1, US-S1-008 | Must | 15. Deduplication & Record Matching | DAT-DDUP | Side-by-side compare with a11y radio group.
US-084 | Done | sprint-0/ddup-tier1 | Must | 15. Deduplication & Record Matching | DAT-DDUP | Merge commit transaction.
US-085 | Not started |  | Must | 15. Deduplication & Record Matching | DAT-DDUP
US-086 | Not started |  | Must | 15. Deduplication & Record Matching | DAT-DDUP
US-087 | Done | sprint-0/ddup-tier1 | Should | 15. Deduplication & Record Matching | DAT-DDUP | Match-model versioning + dual approval.
US-097 | Partial | US-S3-002 | Must | 10. Data Requests & Sharing Management | API-DRS | DRS scaffold; Query Builder UI deferred.
US-098 | Partial | US-S1-008, US-S3-002 | Must | 10. Data Requests & Sharing Management | API-DRS | Sensitivity badges + scaffold; full Field Selector deferred.
US-099 | Not started |  | Must | 10. Data Requests & Sharing Management | API-DRS
US-100 | Not started |  | Must | 10. Data Requests & Sharing Management | API-DRS
US-101 | Not started |  | Must | 10. Data Requests & Sharing Management | API-DRS
US-102 | Not started |  | Must | 10. Data Requests & Sharing Management | API-DRS
US-103 | Not started |  | Must | 10. Data Requests & Sharing Management | API-DRS
US-104 | Not started |  | Should | 10. Data Requests & Sharing Management | API-DRS
US-105 | Done | sprint-0/dih-framework | Must | 16. Data Integration Hub | DIH (ING) | SourceSystem + DPA.
US-106 | Done | sprint-0/dih-framework | Must | 16. Data Integration Hub | DIH (ING) | MappingRule entity.
US-107 | Done | sprint-0/dih-framework | Must | 16. Data Integration Hub | DIH (ING) | ConnectorRun + counts.
US-108 | Done | sprint-0/dih-framework + tween 29799ba | Must | 16. Data Integration Hub | DIH (ING) | Pipeline orchestrator.
US-109 | Not started |  | Must | 16. Data Integration Hub | DIH (ING)
US-110 | Not started |  | Must | 16. Data Integration Hub | DIH (ING)
US-111 | Done | US-S1-004 | Must | 16. Data Integration Hub | DIH (ING) | Fast-track auto-promote with 1% sampling.
US-112 | Not started |  | Must | 16. Data Integration Hub | DIH (ING)
US-113 | Not started |  | Should | 16. Data Integration Hub | DIH (ING)
US-114 | Not started |  | Must | 16. Data Integration Hub | DIH (ING)
US-115 | Not started |  | Must | 16. Data Integration Hub | DIH (ING)
US-116 | Done | S19 (2026-05-15) | Must | 17. Questionnaire Authoring | REF-DATA | VERIFIED 2026-08-08: ChoiceList/ChoiceOption with effective dates, status, ULID, parent_code cascading, deprecate-not-delete, author!=approver constraint; seed migrations 0003-0011; admin UI screens-admin-refdata-choicelists.jsx; DRF /v1/ref-data/choice-lists. Live: 97 lists / 790 options. See docs/audit/2026-08-08_delivery_and_code_health_audit.md
US-117 | Done | S19 (2026-05-15) | Must | 17. Questionnaire Authoring | INT | VERIFIED 2026-08-08: FormSection/FormQuestion/FormSkipLogic/FormConstraint; draft->pending_approval->active->retired with dual approval; immutability via _form_version_is_locked; admin reorder + expression-validation views; scripts/import_legacy_questionnaire.py + migration 0002. Live: 2 versions / 12 sections / 191 questions. See docs/audit/2026-08-08_delivery_and_code_health_audit.md
US-118 | Partial | S19 (2026-05-15) | Must | 17. Questionnaire Authoring | INT (xlsform) | VERIFIED 2026-08-08 — PARTIAL. Done: xlsform_export.export_to_xlsx, admin download, determinism tests. Missing: management command export_xlsform; REST endpoint GET /v1/intake/form-versions/{id}/xlsform; pyxform round-trip test (pyxform is not a dependency); k-forms/build_nsr_xlsform.py NOT retired to scripts/legacy/ — it still lives outside the repo and 19 intake tests skip without it, in CI too. Path is xlsform_export.py, not xlsform/exporter.py. See docs/audit/2026-08-08_delivery_and_code_health_audit.md
US-119 | Partial | S19 (2026-05-15) | Must | 17. Questionnaire Authoring | INT, DAT-DQA, DIH, DAT | VERIFIED 2026-08-08 — PARTIAL. Done: Listener 1 (DAT-DQA) via rule_pack_sync, called inside approve_form_version's atomic transaction, idempotent, audited (rule_pack_synced), tested. Missing: Listener 2 (DIH draft MappingRule per SourceSystem) — intake never references MappingRule; Listener 3 (auto-generated additive canonical migration + deprecated_at); needs_review flagging of rules pinned to the previous FormVersion. Implemented as a direct in-transaction call, not an intake.form_version.activated signal. See docs/audit/2026-08-08_delivery_and_code_health_audit.md
US-120 | Partial | S19 (2026-05-15) | Should | 17. Questionnaire Authoring | DIH (kobo_push) | VERIFIED 2026-08-08 — PARTIAL. Done: kobo_push.publish_form_version, KoboCredential resolution, audit event, asset_uid persisted on partial failure. Missing: management command kobo_push; ConnectorRun row with mode='push'; contract tests against a stubbed Kobo server (happy path + 3 failure modes); Quarantine rows. Located at apps/intake/kobo_push.py, not apps/ingestion_hub/connectors/. See docs/audit/2026-08-08_delivery_and_code_health_audit.md
US-CONSENT-01 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | Purpose catalogue CRUD + dual-approval; audit events; /api/v1/consent/purposes/.
US-CONSENT-02 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | Statement versioning, i18n, one-ACTIVE-per-purpose partial index, is_material re-consent recount.
US-CONSENT-03 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | Intake capture: walk-in form per-purpose section + gate (refused→declined_consent); capture at promotion (web/CAPI/Kobo).
US-CONSENT-04 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | Server-side capture + idempotency. Android/SQLCipher offline client is external (separate repo).
US-CONSENT-05 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | Citizen dashboard live-wired to /api/v1/consent/members/{id}; matrix + withdraw.
US-CONSENT-06 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | Withdrawal flow, idempotent per day, 30-day SLA clock.
US-CONSENT-07 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | DPO withdrawal queue + decisions + bulk rules + hourly Celery SLA-breach sweep.
US-CONSENT-08 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | Reusable ConsentBadgeCluster + per-purpose detail card on household Consent tab (with legacy inference).
US-CONSENT-09 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | AC-CONSENT-* DQA rule pack seeded DRAFT (scripts/seed_dqa_consent_rules.py); DPO ratifies.
US-CONSENT-10 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | AuditEvent per change + ConsentRecordVersion(audit_event_id); integrity = referential completeness (not a 2nd chain).
US-CONSENT-11 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | DIH fast-track synthetic consent from ratified DPA scope; unratified DPA holds promotion.
US-CONSENT-12 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | PMT recompute ELIGIBILITY gate; withdrawn/pending blocks + events.
US-CONSENT-13 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | REF send_referral gate on REFERRAL (blocks withdrawn/refused); blocked_member_ids helper.
US-CONSENT-14 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | DRS extract row-gate: render_bundle excludes blocked members per DSA consent_purposes (SQL layer).
US-CONSENT-15 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | DDUP merge reconciliation (union of grants; withdrawal wins; conflict blocks).
US-CONSENT-16 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | UPD head-change opens REGISTRATION re-capture sub-task.
US-CONSENT-17 | Done | PR #1 (Epic 19) | Should | 19. Consent Management | Consent (SEC) | DPO coverage dashboard stub — live KPI cards, charts deferred.
US-CONSENT-18 | Done | PR #1 (Epic 19) | Must | 19. Consent Management | Consent (SEC) | ADR-0024 + DPIA §14 + docs/openapi/consent.yaml.
US-121 | Not started |  | Must | 17. Questionnaire Authoring | Intake & Registration | UBOS wave intake: store the accepted CSPro instrument as a FormVersion so the review compares against the registry, not an uploaded file. ADR-0034. See docs/stories/US-121-122_ubos_wave_intake.md.
US-122 | Not started |  | Must | 16. Data Integration Hub | Data Integration Hub | UBOS wave intake: an unknown answer code is held as unmapped, never coerced. Needed before the first wave (late Oct/Nov 2026). ADR-0034/0032. See docs/stories/US-121-122_ubos_wave_intake.md.
US-123 | Not started |  | Must | 20. Survey Data Hub Completion & Separation | DIH (ING) / Survey Data Hub | Proposed 22 Sep 2026. See docs/stories/US-123-129_survey_data_hub.md. Foundation; blocks all production Hub promotion.
US-124 | Not started |  | Must | 20. Survey Data Hub Completion & Separation | DIH (ING) / Survey Data Hub | Proposed 22 Sep 2026. See docs/stories/US-123-129_survey_data_hub.md. Extends RawLanding; does not mutate historical payloads.
US-125 | Not started |  | Must | 20. Survey Data Hub Completion & Separation | DIH (ING) / Survey Data Hub | Proposed 22 Sep 2026. See docs/stories/US-123-129_survey_data_hub.md. Builds on US-117..120 and ADR-0034.
US-126 | Not started |  | Must | 20. Survey Data Hub Completion & Separation | DIH (ING) / Survey Data Hub | Proposed 22 Sep 2026. See docs/stories/US-123-129_survey_data_hub.md. Adds issue/review workflow above existing DQA results and DDUP candidates.
US-127 | Not started |  | Must | 20. Survey Data Hub Completion & Separation | DIH (ING) / Survey Data Hub | Proposed 22 Sep 2026. See docs/stories/US-123-129_survey_data_hub.md. Current JSX console is a design harness, not the production UI.
US-128 | Not started |  | Must | 20. Survey Data Hub Completion & Separation | DIH (ING) / Survey Data Hub | Proposed 22 Sep 2026. See docs/stories/US-123-129_survey_data_hub.md. Replaces direct in-process promotion with controlled exchange.
US-129 | Not started |  | Should | 20. Survey Data Hub Completion & Separation | DIH (ING) / Survey Data Hub | Proposed 22 Sep 2026. See docs/stories/US-123-129_survey_data_hub.md. Pilot-readiness gate; depends on US-123..128.

## Forward
Session | Status | Headline | Focus modules | Backlog IDs likely covered
S5 | Planned | Tier 3 probabilistic DDUP scaffold (post-calibration) + UPD review UI wiring (US-090) + PMT v0 weights file | DAT-DDUP, UPD, PMT | US-090, US-091, US-094 polish; partial US-022 weights
S6 | Planned | API-DRS Query Builder UI + Field Selector + Preview + Excel/CSV encrypted delivery | API-DRS, SEC | US-097, US-098, US-099, US-100, US-101
S7 | Planned | DPO cumulative volume console + anomaly detection | API-DRS, SEC | US-103, US-056
S8 | Planned | Citizen-side: receipt SMS, provisional ID lifecycle UX, citizen status check | INT, SEC | US-112 polish, US-065
S8b | Done | Questionnaire authoring + choice-list catalogue (system owns the form) — Delivered early in S19 (2026-05-15): US-116 + US-117 both verified Done 2026-08-08. | REF-DATA, INT | US-116, US-117
S8c | Partial | XLSForm generator + propagation pipeline + Kobo push connector — Partially delivered in S19: US-118/119/120 all Partial 2026-08-08 — see Backlog Status notes for the specific gaps. | INT (xlsform), DIH (kobo_push), DAT-DQA, DAT, REF-DATA | US-118, US-119, US-120
S9 | Planned | CAPI offline tablet flow (after ADR-0004 spike resolves) | INT (CAPI) | US-001, US-002, US-003, US-004, US-081
S10 | Planned | Recertification cycle + bulk-import quarantine UI | UPD, DIH | US-031, US-113
S11 | Planned | Observability dashboards + DR drill + ops runbooks | RPT, SEC, DevOps | US-073, US-074
S12 | Planned | Pilot prep (Karamoja): training material, MGLSD UAT, MVP cut tag | Cross-cutting | MVP closing
S27 | Done | Consent Management foundations: data model, purpose catalogue, statement versioning, intake capture (Web+CAPI), citizen dashboard, badge cluster, DQA rules, audit chain, DPIA addendum — delivered 2026-05-31 (PR #1, ADR-0024) | Consent (SEC), DAT-DQA, INT, SEC | US-CONSENT-01..05, US-CONSENT-08..10, US-CONSENT-18 (partial)
S28 | Done | Consent propagation + withdrawal: ticket flow, DPO queue, DIH fast-track, PMT/REF/DRS/DDUP/UPD integration, coverage dashboard, ADR-0024 — delivered 2026-05-31 (PR #1, ADR-0024) | Consent (SEC), DIH, PMT, REF, API-DRS, DAT-DDUP, UPD, RPT | US-CONSENT-06, US-CONSENT-07, US-CONSENT-11..17, US-CONSENT-18 (close)
S29 | Planned | Survey Data Hub foundation: separate DIH boundary, immutable Kobo archive, form/version lineage, and reviewer workflow. | DIH, INT, DAT-DQA, DAT-DDUP, API, SEC, Platform | US-123, US-124, US-125, US-126, US-127
S30 | Planned | Survey Data Hub integration and pilot readiness: governed NSR exchange, reconciliation, monitoring, retention, and controlled Kobo pilot. | DIH, API, SEC, RPT, Platform | US-128, US-129

## Dependencies
ID | Dependency | Blocks (session) | Owner | Status | Notes
DEP-01 | NITA-U production tenancy | S11 / pilot | MGLSD ICT + NITA-U | Open | Procurement not yet started. Still hard blocker for production cut-over.
DEP-02 | NIRA NIN verification API MoU | S9+ | MGLSD + NIRA | In progress | Mock + client seam (US-S3-006) ship in place. Live MoU still needed before live integration.
DEP-03 | PMT v0 model parameters (TOR weights) | S5 | Statistician + UBOS | In progress | PMT v1 scaffold landed (US-S1-010). Weights file is next.
DEP-04 | PMT v1 calibrated model | Release 2 | Statistician + WB TA | Open | Calibration dataset not yet defined.
DEP-05 | DSA template (outbound) | S6 / pilot | MGLSD Legal + AG Chambers | Open | Partner-side ABAC (US-S4-001) is in place; legal text still needed before live partner sharing.
DEP-06 | DPA template (inbound) | Done (informal) | MGLSD Legal | In progress | DIH SourceSystem + DPA entity scaffolded; legal text still needed.
DEP-07 | Pilot sub-region selected | S12 | NSR Unit | Open | Karamoja recommended; decision pending.
DEP-08 | NSR Unit hired and trained | S12 / pilot | MGLSD HR + NSR Unit | Open | Roles unfilled; training material to follow in S12.
DEP-09 | DPIA approved by national DPO | Pilot go-live | DPO + MGLSD | In progress | Initial draft committed (6ce1d52). Approval cycle yet to start.
DEP-10 | UBOS GeographicUnit dataset (current) | Done | UBOS + REF-DATA | Done | Loader live since sprint-0/ubos-loader.
DEP-11 | UBOS village polygons (AC-GPS-POLYGON) | S9+ | UBOS | Open | Not yet published; fallback to LC1 code applies until then.
DEP-12 | Kobo Toolbox project list + DPAs | Release 2 | M&E + partner agencies | Open | Per-project DPAs needed.
DEP-13 | WFP SCOPE technical contact + data sample | Release 2 | WFP Uganda | Open | Outreach pending.
DEP-14 | USSD aggregator partnership + short code | Release 2 | MGLSD + UCC + telco | Open | Short-code procurement non-trivial.
DEP-15 | CAPI form runtime decision (ADR-0004) | S9 | Architecture + Procurement | Open | Spike not yet run. Server-side intake (US-S2-006) is runtime-agnostic so far.
DEP-16 | Match model calibration dataset (DDUP) | Release 2 | UBOS + WB TA | Open | Calibration not started. Tier 1 + tier 2 deterministic matching are live.
DEP-17 | Threat model workshop | Done | Architecture + Security | Done | Documented at docs/threat_model.md (6ce1d52).
D-19 | US-116 ChoiceList catalogue active | S8b | REF-DATA | Resolved | RESOLVED 2026-08-08: ChoiceList catalogue is active — 97 ChoiceLists / 790 ChoiceOptions seeded by reference_data migrations 0003-0011. No longer blocks US-117 (also delivered). Was stale since S19 (2026-05-15).
D-20 | US-117 Questionnaire authoring active | S8c | INT | Resolved | RESOLVED 2026-08-08: questionnaire authoring is active — 2 FormVersions, 12 sections, 191 questions, admin authoring UI, dual-approval lifecycle. Does NOT block the S9 CAPI runtime decision (ADR-0004 / DEP-15) any longer. Downstream US-118/119/120 are Partial for their own reasons, not for want of this. Was stale since S19.
D-21 | ADR-0004 CAPI runtime must consume FormVersion JSON or generated XLSForm | S9 | INT (CAPI) | Open | Constrains the CAPI build-vs-buy choice.
DEP-22 | DPO sign-off on purpose catalogue (CONSENT-O-01) | S27 | DPO + MGLSD Legal | Resolved | RESOLVED 2026-05-30: scope-doc 9 incl. ELIGIBILITY seeded (migration 0002). DPO production sign-off still required before flag-on.
DEP-23 | DPO sign-off on withdrawal SLA (CONSENT-O-03) | S28 | DPO + NSR Coordinator | Resolved | RESOLVED 2026-05-30: 30 days adopted (DPPA §29). DPO production sign-off still required before flag-on.
DEP-24 | DPA ratification model decision (CONSENT-O-08) | S28 | DPO + DIH team | Resolved | RESOLVED 2026-05-30: one ratification at DPA activation. DIH fast-track (US-CONSENT-11) built to it.
DEP-25 | Citizen portal Keycloak realm | S27 (stub) / Release 3 (live) | NSR MIS Architecture | Partially resolved | Stub auth delivered (citizen portal /portal/consent/). Keycloak realm still a Release-3 follow-up.
DEP-26 | Real translated statement copy (6 languages) | S27 | NSR Coordinator + DPO | Open | Statement v3 seeded with English real text + 6 placeholders flagged is_placeholder=True.
DEP-27 | Kobo pilot DPA, project access, and approved encrypted raw/attachment archive location | S29 / S30 | MGLSD Legal + DPO + Kobo project owner + NITA-U | Open | Required before live Kobo credentials, attachment archive, or promotion are enabled. Archive-only technical testing may use synthetic data only.
DEP-28 | NSR internal promotion API security and exchange-contract sign-off | S30 / pilot | NSR MIS Architecture + Security + DPO | Open | Must define service identity, network boundary, idempotency, sensitive-log policy, error contract, and reconciliation owner before production promotion.

## Notes
NSR MIS Sprint Plan v0.3
Date | 30 May 2026
Owner | Sprint Plan v0.2 (15 May 2026)
Supersedes | Sprint Plan v0.1 (14 May 2026)
TERMINOLOGY
v0.1 used 'Sprint' to mean a 2-week calendar iteration with 7.5 FTE capacity. The repo's commits use 'Sprint' to mean a Claude Code work session lasting hours. These are different things.
From v0.2 forward, this plan distinguishes:
• Session — a Claude Code work batch (S0, S1, S2, ...). Hours, not weeks. Commits prefixed US-S<n>-<seq>.
• Calendar sprint — a human team iteration (2 weeks). Not used in this v0.2 yet because the team has been outpacing any 2-week schedule. Re-introduce when human review/UAT cycles become the bottleneck.
RECONCILIATION SUMMARY
Sessions S0-S3 are Done. Session S4 is in progress (3 of N stories so far).
55 commits across 5 sessions. ~1,861 lines of model code across 12 modules. 21 migrations. 17 test files.
5 ADRs in repo (0001-0005). 0005 is new from S1 (sub-region partitioning).
Threat model + DPIA initial drafts committed in Sprint 0.
BACKLOG STATUS
Done | 49 of 114 stories
Partial | 7
Not started | 58
FROM v0.1 — what changed
Sprint Plan v0.1 had 39 calendar sprints over 18 months at 7.5 FTE. v0.2 acknowledges that Claude Code session velocity is roughly 10x higher and reorganises as sessions.
DEP-10 (UBOS GeographicUnit loader) and DEP-17 (Threat model workshop) are now Done.
DEP-02 (NIRA), DEP-03 (PMT v0), DEP-06 (DPA), DEP-09 (DPIA) moved from Open to In progress.
7 backlog stories are partial — they have scaffolds but UI wiring or polish is pending, and the reporting surface now includes live dashboards, exports, and record-level drill-downs.
WHAT TO DO NEXT
1. Treat sessions S5-S12 as the residual scope. Likely 1-2 days each at current velocity.
2. Reopen a calendar plan only when external dependencies (DEP-01 NITA-U tenancy, DEP-08 hiring, DEP-09 DPIA approval) become the bottleneck. The team's coding velocity is no longer the constraint.
3. Watch DEP-05 (DSA), DEP-09 (DPIA approval) and DEP-01 (NITA-U). They gate pilot, not code.
4. ADR-0004 (CAPI form runtime) still Proposed. The CAPI offline flow (S9) needs the decision before then.
FILES
Source backlog: docs/03_backlog.xlsx
SAD: docs/01_solution_architecture.docx
ADRs: docs/adr/0001..0005
Threat model: docs/threat_model.md
DPIA draft: docs/dpia.md
This file: docs/08_sprint_plan.xlsx (v0.2)